CITY OF LONDON · ONTARIO

THE PUBLIC-RECORDS
LEDGER

Executive Findings Brief

A source-locked municipal accountability review
Final Public Edition 5.0

| 12 / 12 research asks dispositioned No placeholder modules | 8 built from public records Complete at published depth | 4 records-dependent Filing-ready requests supplied |
| --- | --- | --- |

Prepared by Raj Gandhi

Evidence lock: August 20, 2026

Independent review - not an official audit or assurance engagement

EXECUTIVE FINDINGS | 01

# Executive verdict

What the public record establishes - and what it does not.

THE GOVERNING CONCLUSION The record supports a material disclosure-and-performance-measurement problem. It does not, by itself, establish fraud, corruption, favouritism, or waste. The strongest next move is targeted disclosure and traceable reconciliation - not allegation.

Overall strength. Strong as a source-locked accountability brief; moderate as a transaction audit. It can establish disclosure gaps, reconcile published totals, reproduce arithmetic, and identify control findings already made by MNP. It cannot certify the books or test non-public invoices, bid evaluations, amendments, payroll, HR, or project-control records.

## Six highest-value findings

1. Procurement visibility. 1,394 of 1,978 scraped posted-award records - 70.5% - carried no visible value. This is not total City procurement.

2. Infrastructure renewal. The $946.1M maintain-current gap was 66.3% above 2019 and 103.0% above 2014; it is a modeled need, not proof of misspending.

3. DC reserves. 2025 contributions were $68.5M, disbursements $106.2M, and closing balance $327.1M. Sensitivities are not forecasts.

4. PSAB variance. The 2025 annual surplus was $463.734M against a $281.085M budget. The $182.649M variance is not unrestricted cash.

5. Community grants. The complete 2024-2027 ledger contains 42 recipients and exactly $9.2M in allocations; two MNP control findings remain open.

6. Housing stages. Permits, tracked units, in-progress units, planned units, completions, and occupancy are separate measures.

SOURCE LOCK  S01-S24 · C001-C037

EXECUTIVE FINDINGS | 02

# How to read the evidence

Five tests keep the language inside the source.

| Test | Rule | Application |
| --- | --- | --- |
| 1 | Primary source | Official City, board/commission, provincial disclosure, or agenda attachment. |
| 2 | Scope | Period, entity, unit, support type, and population are explicit. |
| 3 | Status | Approval, budget, award, commitment, payment, completion, and outcome remain distinct. |
| 4 | Reproduction | Displayed arithmetic can be recalculated from cited inputs. |
| 5 | Language | Interpretation does not outrun the source; material limits sit beside the claim. |

## Evidence labels

| Label | Meaning | Permitted use |
| --- | --- | --- |
| VERIFIED | Scope-matched source fact | May be stated as sourced fact |
| DERIVED | Arithmetic from verified inputs | Show the calculation |
| LIMITED | Valid only at narrower scope | Keep limitation adjacent |
| REQUESTED | Required input not public | No substantive conclusion |
| CORRECTED | Earlier wording superseded | Use the current source-locked wording |

NO FALSE COMPLETION A module may be finished even when the public record cannot support a transaction-level conclusion. Completion means the test, denominator, source gap, record-holder, and requested fields are specified - not that missing evidence may be guessed.

SOURCE LOCK  Methodology; Appendix E public-use rules

EXECUTIVE FINDINGS | 03

# Financial baseline and condition

Large numbers require the correct accounting and support-type labels.

| $1.468B 2026 property-tax operating expense $926.085M levy | 3.4% 2026 rate increase Down from prior 6.4% | $5.764B 10-year capital plans Three support types |
| --- | --- | --- |

## Three signals - three different questions

| Area | Published figures | Screen | Guardrail |
| --- | --- | --- | --- |
| Infrastructure | $946.1M maintain-current gap | +66.3% vs 2019 | Modeled renewal need; not current failure |
| PSAB surplus | $463.734M actual vs $281.085M budget | +$182.649M | Not tax-supported cash surplus |
| DC reserves | $68.5M in; $106.2M out | -$37.7M in 2025 | Balance is not free capacity |

The capital plan totals are $3.588B property-tax supported, $707M water supported, and $1.469B wastewater-and-treatment supported. These support types should never be collapsed into an unlabeled total.

## DC sensitivity - arithmetic, not forecast

| Scenario | Annual net change | Year-3 balance | Interpretation |
| --- | --- | --- | --- |
| Repeat 2025 | -$37.7M | $214.0M | Observed relationship held constant |
| High stress | -$62.0M | $141.1M | Contributions -20%; disbursements +10% |
| Recovery | -$17.1M | $275.8M | Contributions +30% |

DO NOT CALL THIS A FORECAST The scenarios ignore project closures, new approvals, interest, debt issuance, exemption changes, and timing. They are sensitivity tests only.

SOURCE LOCK  S01, S04, S09-S13 · C001-C009, C017-C019

EXECUTIVE FINDINGS | 04

# Capital projects: the missing join

The recurring public-record issue is reconciliation, not a recurring overrun finding.

Public sources often provide a budget, financing line, or status update without a stable project ID connecting all three to the award, amendments, forecast-at-completion, physical progress, and closeout.

| Dossier | Public amount | Unresolved test | Route |
| --- | --- | --- | --- |
| Highbury Facility | $301.9M / ~$321.7M vintages | Budget-vintage and delivery reconciliation | R1 |
| Roadmap to 3,000 | $78.0M project book | Cost per completed/occupied unit | R4 |
| Fanshawe grant | $20.75M | Agreement, payment, milestones, closeout | R1/R6 |
| Mud Creek 2B | $24.720M | Award, amendments, FAC, completion | R1/R2 |
| Springbank Dam | $14.6M stage; up to $3M decommission | Final cost and closeout certificate | R1 |
| Wharncliffe/Horton | $90M; $39.6M gap | Estimate, financing plan, schedule | R1 |
| Contingency reserve | $35.18M / $96.59M / $109.8M | Fund mapping and policy target | R6 |
| 401 / Highway 4 | No City cost established | Closed unless a City project is specified | Closed |

CAPITAL CONCLUSION The named files show a recurring reconciliation gap. They do not establish a recurring pattern of overruns. R1 asks for stable IDs and the budget-award-amendment-payment-progress-closeout spine.

SOURCE LOCK  S01, S02, S09, S10, S25-S27 · R1, R2, R4, R6

EXECUTIVE FINDINGS | 05

# Procurement: visibility is not compliance

The posted portal supports a disclosure finding, not an award-by-award misconduct conclusion.

| 70.5% records without visible value 1,394 of 1,978 | $1.022B known-value pool 584 records only | 71.6% top-ten known-value share Partial disclosed slice | 94.3% construction share Known-value dollars |
| --- | --- | --- | --- |

The denominator is incomplete by design. The known-value pool cannot stand in for total City procurement. HHI is retained only as a descriptive sensitivity statistic for this partial population; it is not a relevant antitrust market or a conclusion about competition.

| Test | Result | Reason | Evidence |
| --- | --- | --- | --- |
| Policy version | PASS | Legacy/current boundary identified | S06-S07 |
| Annual compliance review | PASS | 2025 review received | S07 |
| Biannual reporting | PASS | May 2026 report located | S08 |
| Limited tendering | PARTIAL | Portal lacks complete row-level flag | R2 |
| Amendments | NOT TESTABLE | No joined amendment history | R2 |
| Bid spread / disqualification | NOT TESTABLE | Bid tabulations required | R2 |
| Award-value publication | DISCLOSURE FAIL | 70.5% no visible value | S05 |

REPRODUCIBILITY BOUNDARY The original 1,978-row parser export and normalization workbook were not recovered. C010-C013 remain derived / limited. This package replays their arithmetic but cannot regenerate their source population.

SOURCE LOCK  S05-S08 · C010-C016 · R2

EXECUTIVE FINDINGS | 06

# Workforce and service performance

The public salary layer is useful, but it is not the municipal workforce denominator.

| 579 -> 831 salary-disclosure population +43.5%, 2021-2025 | $74.4M -> $109.0M disclosed compensation +46.5% | $127.5K -> $129.7K average disclosed salary +1.7% nominal |
| --- | --- | --- |

The Sunshine List cannot answer total FTE growth, management ratio, spans, layers, vacancies, overtime, turnover, sick time, contracted labour, or output per FTE. Heuristic title buckets are screening labels only.

## Finished productivity specification

| Metric | Numerator | Denominator | Required source |
| --- | --- | --- | --- |
| Management ratio | Official management FTE | Total active FTE | HR complement |
| Span of control | Direct reports | People managers | Position hierarchy |
| Vacancy rate | Budgeted less filled FTE | Budgeted FTE | Monthly complement |
| Overtime burden | Overtime hours/cost | Worked hours/payroll | Payroll by service |
| Turnover | Separations | Average headcount | HR movement file |
| Service productivity | Volume and quality | FTE and cost | KPI + finance + HR |

WHAT IS BUILT Transit and police have evidence-built modules. Fire, water, wastewater, roads, recreation, fleet, IT, real estate, and legal/risk each have a defined KPI spine and request route. No unsupported cross-service ranking is made.

SOURCE LOCK  S28, S31-S35 · C020-C021, C038-C044 · R3, R5

EXECUTIVE FINDINGS | 07

# Housing and homelessness

A pipeline is not a completion count; a permit is not an occupied home.

| Indicator | Figure | Stage / scope | Does not prove |
| --- | --- | --- | --- |
| Residential permits | 5,462 | All permitted units | Not starts, completions, or occupancy |
| HAF year-2 permits | 4,284 vs 3,991 | Measurement window | Not completed HAF homes |
| City-funded affordable tracked | 2,576 | Since late 2021 | Mixed pipeline stages |
| In progress | 675 | Tracked subset | Definition may vary |
| In planning | 1,360 | Tracked subset | Not approval or construction |
| City-led HSH occupied | 44 | Explicit completion/occupancy | Specific subset only |
| HSH tracked | 422 | Combined pipeline | Not all complete |

AFFORDABLE-HOUSING RECONCILIATION The 675 in-progress and 1,360 planned units total 2,035, leaving 541 of the 2,576 City-funded tracked units in other stages not broken out in the summary. That is a classification question, not an error finding.

## Hubs: better cost evidence, incomplete cohort evidence

MNP reported approximate bed-day costs of $120.93 for shelter, $207.25 for Atlohsa, and $362.34 for YOU, plus more than 100 people served and more than 40 stable-housing outcomes. The record still lacks a location-level cohort, retention, length-of-stay, and critical-incident ledger.

BALANCED FINDING The February 2026 supplement materially improves the evidence. It does not close the project-level cohort and retention questions. R4 asks for the missing join.

SOURCE LOCK  S02, S03, S17-S19, S23 · C022-C028, C035-C037 · R4

EXECUTIVE FINDINGS | 08

# Grants, incentives, and internal audit

The allocation ledger is complete; agreement-level payments and outcomes remain the next layer.

| 42 multi-year recipients Complete published list | $9.2M four-year allocation $2.3M per year | 164,003 people served / year Program-reported average | >$50M other funding leveraged Program-reported |
| --- | --- | --- | --- |

Approval and allocation are not payment. The City's impact report says recipients were meeting expected outcomes at the reporting date; this review does not independently certify those program-level results.

## Two open MNP control findings

Score-to-award rule. No documented threshold or criteria translates final application scores into funding amounts; the management action remains on track for Q4 2027.

Scoring rationale. SmartSimple did not require panel members to enter rationale; the strengthening action remains on track for Q4 2027.

## Audit-to-ledger connection

| Audit | Volume | Core issue | Status at lock |
| --- | --- | --- | --- |
| Community Grants | 2 medium | Score/funding rule; rationale | Q4 2027 on track |
| Homelessness | 2 medium | Hubs governance/outcomes | Supplement added |
| CIPs | 10 observations | Outcome monitoring and mapping | Q3 2026-Q2 2027 |
| CEAP | 17 observations | Measurability, funding, ownership | Action follow-up needed |
| Performance Measurement | Final Nov. 2025 | Corporate framework | Completion target Q4 2026 |

SOURCE LOCK  S14-S16, S20-S24 · C029-C034, C045-C047 · R6

EXECUTIVE FINDINGS | 09

# The reform is a public ledger

Disclosure architecture can convert scattered reporting into traceable management information.

BEST SINGLE QUESTION Will administration publish, for every major capital project and incentive program, one machine-readable row connecting original authority, current budget, award, amendments, committed amount, paid amount, schedule, output, and closeout status?

| # | Ledger | Minimum spine | Cadence |
| --- | --- | --- | --- |
| 1 | Major-project reconciliation | Authority, budget/schedule, FAC, award, amendments, payments, progress, closeout | Quarterly |
| 2 | Procurement award + amendment | Vendor, value, bids, authority, policy, exceptions, amendments, performance | Monthly |
| 3 | Grant/CIP outcomes | Score, rationale, approved/paid, milestones, outcome, closeout, clawback | Annual + live |
| 4 | Housing cohort pipeline | Application through occupancy and affordability under stable IDs | Monthly |
| 5 | Workforce complement | Budgeted/filled FTE, vacancies, layers, spans, overtime, turnover | Quarterly |
| 6 | Service KPI dictionary | Baseline, target, actual, cost, quality, source, owner, revision history | Quarterly data |
| 7 | Internal-audit actions | Observation, management action, owner, dates, evidence, closure rationale | Each cycle |

MOTION-READY DIRECTION That Civic Administration report back with a public, machine-readable municipal accountability ledger linking major capital projects, procurement awards and amendments, grants/CIP incentives, and housing investments to authority, financing, payment, schedule, output and closeout status; and identify fields that cannot be published and the legal basis for each exclusion.

SOURCE LOCK  Part 11 reform sequence · Companion workbook: Reforms

EXECUTIVE FINDINGS | 10

# R1-R6: the transaction-level follow-through

Six filing-ready routes turn unknowns into defined evidence requests.

| Route | Subject | Core records | Period |
| --- | --- | --- | --- |
| R1 | Capital controls | Budgets, FAC, schedules, changes, progress, closeout | 2014-2026 |
| R2 | Procurement | Bids, exceptions, award values, amendments, performance | 2017-2026 |
| R3 | Workforce | FTE, hierarchy, vacancies, movements, overtime, contractors | 2019-2026 |
| R4 | Housing/Hubs | Stable project IDs, stages, contributions, anonymized outcomes | 2021-2026 |
| R5 | Service KPIs | Cost, volume, quality, timeliness, reliability, utilization | 2019-2026 |
| R6 | Grants/CIPs | Requested, scored, approved, committed, paid, outcomes, closeout | 2020-2026 |

## 90-day implementation sequence

| Window | Action | Deliverable |
| --- | --- | --- |
| Days 0-30 | File R1-R6; index first, fee estimates, rolling native production | Custodians, search terms, production schedule |
| Days 31-60 | Normalize IDs, rebuild joins, send factual questions | Project, procurement, grant, housing master tables |
| Days 61-90 | Publish exceptions with City responses and versioned calculations | Edition 5.1 transaction supplement |

PRIORITY ORDER 1) capital controls and amendments; 2) procurement bid/amendment join; 3) housing/grant project outcomes; 4) workforce and service productivity. This order targets the greatest risk of public misinterpretation first.

SOURCE LOCK  Appendix A · R1-R6 · 90-day plan

EXECUTIVE FINDINGS | 11

# How to use the package

The brief is the entry point; the evidence trail remains the authority.

## Safe wording

| Use | Avoid |
| --- | --- |
| The 2026 budget update reports... | The City spent... when the source is authority |
| Of 1,978 posted awards scraped... | Of all City procurement... |
| The Sunshine List disclosure population... | City headcount or management complement |
| Permitted / planned / completed / occupied | Homes built for mixed stages |
| The record lacks an end-to-end reconciliation | Fraud, corruption, favouritism, or waste |

## Release map

Executive brief. The 12-page decision and outreach layer.

Final Public Edition 5.0. The canonical 40-page public report.

Evidence book. The 135-page expanded research and source-lock record.

Companion workbook. Claims, sources, calculations, dossiers, crosswalks, and R1-R6 in machine-readable form.

Reproducibility repository. Deterministic CSV extraction, calculation replay, tests, corrections, and publication rules.

Microsite prompt. A production specification for the public evidence explorer.

PUBLICATION RULE Use only Final Public Edition 5.0 and later source-locked supplements for outreach. If a source changes, update the claim register and preserve the prior version rather than silently overwriting the evidence trail.

## Selected source spine

S01 2026 Annual Budget Update · S02 2025 Annual Development Report · S04 Corporate Asset Management · S05 Bids and Tenders portal · S10 2025 DC Reserve Funds report · S12 2025 Consolidated Financial Statements · S14 Community Grants Program · S16 Grants audit follow-up · S19 Housing & Homelessness supplement · S22 CEAP audit · S24 Audit Committee follow-up · S31 LTC Annual Report · S32 LPS Annual Report.

SOURCE LOCK  Complete 37-source register and URLs are provided in the companion workbook and repository.